## Sheet1
Done
Work in progress
To Do
|  | Assignee | Title | Description | Expected time | Time taken | Date? | Status
| 1 | Abdallah | Create a stage to play | Create prefabs for the tiles, make it nature-inspired/organic. Populate the surroundings of the stage with natural “objects”; give it a similar vibe to Trails in the Sky | 1h | 2h | 2019-03-12 | Done
| 2 | Abdallah | Create part members | 2 members for now. Design their stats | 1h | 0.2h | 2019-08-12 | Done
| 3 | Hoang | Create enemy units | 2 members for now. Design their stats | 1h | 0.2h | 2019-08-12 | Done
| 4 | Both | Implement mouse cursor navigation | Allow the player to navigate the stage with mouse clicks, all while accounting to the unit’s movement and attack range stats | 18h |  |  | Work in progress
| 5 | Abdallah | (From Task 4) Implement Movement System | Implement the moving system from Sokoban/Pacman (single tile movement) | ?? | 2h | 2019-08-12 | Done
| 6 | Abdallah | (From Task 4) Implement Move for attacks | Take into account the attack range stat of the unit before moving; unit should move until he is in range, then it stops | ?? | 5h | 2019-09-12 | Done
| 7 | Both | (From Task 4) Make sure cursor behaves correctly | Cursor should work only when choosing where to attack/move Cursor should take the selected tile as an object and extract all the necessary data from it (done, 1 hour) | ?? |  |  | Work in progress
| 8 | Hoang | Create UI | Create and add functionality to the buttons. Display the current unit’s stats in the UI | 13h |  |  | Work in progress
| 9 | Hoang | (From Task 7) Create and add functionality to the buttons. | Create and add functionality to the buttons. |  |  |  | Work in progress
| 10 | Hoang | (From Task 7) Display the current unit's stats in the UI | Display the current unit's stats in the UI | ?? | 4h | 2019-09-12 | Done
| 11 | Abdallah | Create AI system for enemy units | Base the behavior of the enemy on the HP of the party members | 4h |  |  | Work in progress
| 12 | Abdallah | Create attack command for units | Design and implement single-unit regular attacks for party and enemy | 10h |  |  | To Do
| 13 | Both | Implement turn system for battle | Base the order on the speed stat of each unit initially. Then, based on the speed stat, fill the “Turn bar” of each unit | 14h |  |  | To Do
| 14 | Hoang | reate defend command for units | Defending increases the speed of the character temporarily Speed must be reset when the next turn arrives | 6h |  |  | To Do